Solar Seminar 2009/2010 Video Documentation and Release Proposal - DRAFT

Introduction/Background

Solar Energy Society of Canada, Northern Alberta Chapter (SESCI-NAC) hosts a monthly, one-evening seminar series at Telus World of Science (Edmonton). To widen the audience potential of these popular events and enhance the SESCI-NAC mission of educating the public about solar energy issues, Barb Allard, producer of the Made-in-Alberta series has created this proposal for video documentation and sharing of the information presented at these seminars.

NB. Barb is a board member of SESCI-NAC and does some volunteer tasks in that capacity. These do not form part of this proposal.

Proposed treatment of the Solar Seminars

Barb and company will videotape the seminar each month to capture the presentation (not including questions) with high-quality sound. They will interview the speaker to create a one-to-three -minute short excerpt, which will be written by Barb Allard and play on Made-in-Alberta on Shaw TV, WebTV and DVD.

RBCC editor takes the speaker’s slide or PowerPoint presentation and edits this onto the audio timeline. Then, he creates rough-cut DVD of one-minute short and full presentation for approval by speaker, Upon approval, RBCC editor divides the video into 10-min chapters and prepares them for export to DVD and YouTube. RBCC web master uploads YouTube videos and creates SolarAlberta page with video embedded.

All footage is shot in broadcast quality, standard definition, digital video. RBCC web hosting and coverage on Edmonton community television is included. Five copies of DVD are also included. Graphic design, visual identity is also included.

Releasing

Solar Seminars are released in the following ways. All costs for releasing are included.

- uploaded to YouTube, videos embedded on one web page

- DVD created, containing one-minute excerpt and full program

- one-minute excerpt aired on community television on Made-in-Alberta show

Deliverables and Quote: price per episode pending

- ten Solar Seminars released, one per month Oct 2009 to July 2010

- ten one-minute short features, covering a range of energy efficiency and renewable energy topics

- SolarAlberta WebTV presence

Timeline: December 2008 – February 2010

10 seminars released on DVD and web, one per month Oct 2009 to July 2010

SolarAlberta WebTV updated once per month, Oct 2009 to July 2010

10 short programs released one per month on Made-in-Alberta through Season Three

- end -